## Sheet 1 - PG&E HELICOPTER REQUE
PG&E HELICOPTER REQUEST
Project Name: | Humboldt Trinity 115kV NERC
Third Party Contractor: | (x1) Medium (x1) HEC (x1) Heavy Lift
Requestor contact name and contact Info: | Adam Peart (480) 234-7842
Foreman Name and contact Info: | Don Clore (480) 266-7074
PGE Project Manager name and contact info: | Fadie Masri (FHM3) (415) 8056773
PGE Line of Business (e.g. Distribution, Transmission) | Transmission
Project Foreman and Contact Info: | Don Clore (480) 266-7074
Project Date(s): | Medium Ship - 8/1/19 - 8/12/19 HEC Ship - 8/13/19 - 8/27/19, 9/15/19 - 9/31/19 Heavy Ship - 8/13/19 - 8/27/19, 9/15/19 - 9/31/19
Daily Start Time: | 7:00
Landing Zone Physical Address (or cross street/landmark) and Coordinates for Aircraft (arrival location): | Rifle Range LZ - 40.727673°, -123.039520° Junction City LZ - 40.764541°, -123.100784° Big Flat LZ - 40.741769°, -123.209122° Big Bar Dump LZ - 40.734882°, -123.259856°
Work Location Coordinates: | See attached KMZ & work locations breakdown
Circuit/Line Name (s): | Humboldt Trinity 115kV
Structure number(s): | See attached work locations breakdown
Detailed Scope of Work: | Medium Ship - Assistn hand dig crews to fly small tools and compressors HEC - Fly men, small tools, insulators Heavy Ship - Fly poles, gravel bags
If job includes pole sets, include height, class and weight of EACH pole: | See attached work locations breakdown
Max Load Weight: | Medium Ship - 2200# HEC - 500# Heavy Ship - 4500#
HEC: | Yes, two-man chair
Type of Cargo being lifted: | Men, poles, gravel bags, compressors, small tools, etc.
Radio Frequencies to be used: | Channel 1, 151.505-TX-RX Tone 74.4 Channel 2, 151.625-TX-RX Tone 74.4
Charge/PM#: | 74000737
Additional Details or Information: | Coordinate with General Foreman for LZ location