SECTION 7                                        Part 135 GH 4A   Part 133 GH 4L

Congested Area Plan

Operator:	Guardian Helicopters, Inc

67 D STREET

Fillmore CA. 93015

Phone (818) 442-9904

FAX   (818) 442-9901

PROJECT: 	EDISON POLE REPLACEMENT   	WORK ORDER #: TD 1524198

ADDRESS: W AVE W 6 AND HISEY RANCH ROAD   ACTON   CA

LZ STAGING AREA  LATITUDE 34°28'40.87"N LONGITUDE 118°13'49.81"W

4154700E LATITUDE 34°29'21.42"N LONGITUDE 118°14'13.44"W45 CL 2 WOOD 1800 LBS

4154699E LATITUDE 34°29'18.68"N LONGITUDE 118°14'13.24"W 50 CL 1 COMPOSITE 1500 LBS

4154698E LATITUDE 34°29'17.24"N LONGITUDE 118°14'13.11"W 45 CL1 COMPOSITE 1300 LBS

4154697E LATITUDE 34°29'14.65"N LONGITUDE 118°14'12.84"W 45 CL1 COMPOSITE 1300 LBS

4154696E LATITUDE 34°29'14.43"N LONGITUDE 118°14'9.61"W45 CL1 COMPOSITE 1300 LBS

CONTACT AT SITE;   BRENNAN RHODES            	     PHONE#: 951-692-8906

CONTRACTOR: HOTLINE CONSTRUCTION EDISON PHONE#: 951-692-8906

PILOT’S NAME(S): 	1.  JOHN OLSON 			CERT #: 2769166

2. BUCKEY MACKAY	 	CERT #: 2778051

3. MICHAEL KLINK 		CERT# 3018828

4. IAN GOODALE			CERT# 3741973

TYPE OF AIRCRAFT:BELL UH-1H	 N# N711GH	A/C CATEGORY: RESTRICTED

BELL UH-1H	 N# N214KK	A/C CATEGORY: RESTRICTED

BELL 407	 N# N407GH	A/C CATEGORY: STANDARD

BELL 205A1	 N# N216GH	A/C CATEGORY: STANDARD

AS350 B2	 N# N498PT	A/C CATEGORY: STANDARD

AS350 B3	 N# N718GH	A/C CATEGORY: STANDARD

AS350 B3	 N# N215GH	A/C CATEGORY: STANDARD

IF SAFETY DICTATES AND OR THE CUSTOMER REQUESTS ADDITIONAL LIFTS THE LIFTS WILL BE CONDUCTED REMAINING WITHIN THE APPROVED TIME PARAMETERS.

TYPE OF LIFTS:  5 EQUIPMENT BAGS 1200 LBS ( 5)  LBS (5)  LARGEST 1800 LBS  CLASS OF LOAD:EXTL CL B  TYPE OF ITEM LIFTING: POLE       AERODYNAMIC   NON- AERODYNAMIC  	 MAX  2000 LBS NO. OF LIFTS: 15	LONG LINE:	 	(NO)	XXX	(YES)	LESS THEN 100 FT 	(LENGTH)

OPERATIONAL ALTITUDE: < 250    STREET CLOSING:  	  (N0)	XX	(YES)

DATE AND TIMES OPERATION WILL BEGIN AND TERMINATE:

| FLIGHT DATES |  | TIME BEGIN | TIME END |  | TODAY’S DATE |
| --- | --- | --- | --- | --- | --- |
| 2-13-2020 |  | SUNRISE | SUNSET |  | 1-24-2020 |
| AGENCY NAME: |  | PHONE#: | PERSON NOTIFIED: |  | DATE: |
| LOS ANGELES COUNTY FIRE | 661-268-0638 |  |  | STATION 81 | NOTIFY |
| PALMDALE SHERIFF STATION | 661-272-2400 |  |  | DISPATCH | NOTIFY |

Evacuation 					Crowd Control 			Street Closure

□No Evacuated Structures 			Operator 			Yes □ No

- Evacuated Structures 	      		 Contractor		Contractor

□Operator

SECTION 7                                        Part 135 GH 4A   Part 133 GH 4L

Congested Area Plan

Operator:	Guardian Helicopters, Inc

67 D Street

Fillmore, California 93015

LIST OF BUILDINGS THAT SHALL EITHER BE PARTIALLY OR ENTIRELY UNOCCUPIED PERSONS ALSO HOMES THAT WILL BE NOTIFIED OF ACTIVITY:

| BUILDING DESCRIPTION/ADDRESS | REMARKS | METHOD |
| --- | --- | --- |
| WEST AVENUE W6 NUMBER UNKNOWN | VACANT DURING OPS | HAND DELIVER |
| HISEY RANCH ROAD NUMBER UNKNOWN | VACANT DURING OPS | HAND DELIVER |
| ALL HOMES WITHIN RED OPERATING AREA | VACANT DURING OPS | HAND DELIVER |
| SEE DIAGRAM = VACANT | VACANT DURING OPS | HAND DELIVER |

Narrative description of pick-up site, route, delivery site, and plan for ceasing operation if unauthorized persons enter operational area or real hazard occurs.

SITE INSPECTION NOTES

ONLY PERSONNEL ESSENTIAL TO COMPLETING THE JOB SAFELY WILL BE PERMITTED TO PARTICIPATE IN THE EVOLUTION. ONLY PERSONNEL PARTICIPATING IN THE SAFETY BRIEF WILL BE PERMITTED TO BE IN THE AREA OF OPERATIONS. ONLY AUTHORIZED ESSENTIAL PERSONAL WILL BE PERMITTED IN THE IMMEDIATE AREA OF OPERATIONS. IN THE EVENT AN UNAUTHORIZED PERSON ENTERS THE OPERATIONS AREA OR A POTENTIAL HAZARD IS IDENTIFIED THE PILOT WILL HOLD THE AIRCRAFT IN RELATIVE POSITION. THIS WILL BE ACHIEVED WITHOUT OVER FLYING THE GROUND CREW. ALL OPERATIONS WILL BE CEASED UNTIL THE PROBLEM IS RECTIFIED.  IN THE EVENT OF AN AIRCRAFT EMERGENCY, THE PILOT WILL RADIO GROUND PERSONNEL AND WILL ATTEMPT TO LAND IN THE EMERGENCY LANDING AREA.

DURING THE LIFT EVOLUTION THE AIRCRAFT AND GROUND CREW WILL ALL BE IN RADIO COMMUNICATIONS. IN THE EVENT OF LOSS COMMUNICATIONS, THE CREW WILL USE STANDARD HAND SIGNALS TO COMMUNICATE WITH THE PILOT. WHEN THE PILOT IS CLEAR HE WILL MOVE THE AIRCRAFT TO A SAFE LOCATION TO ALLOW THE COMMUNICATION PROBLEM TO BE RECTIFIED.

THE OPERATIONS AREA IS WITHIN THE SECURED AREA. ALL ESSENTIAL CREW WITHIN THE OPERATIONS AREA WILL NOT BE INVOLVED IN TAKING PICTURES OR ANY OTHER USE OF CELL PHONES.

PRIOR TO BEGINNING OPERATIONS, A TAILBOARD SAFETY BRIEF WILL BE CONDUCTED.

- HELICOPTER WILL LAND AT THE LZ TO CONNECT THE LONGLINE AND CONDUCT A TAILBOARD SAFETY BRIEF

- POLES WILL BE STAGED AT STAGING AREA

- FUELING WILL OCCUR AT THE LZ

- EMERGENCY LANDING ZONE IS AT THE STAGING AREA AND ALONG THE FLIGHT PATH

- TAILBOARD SAFETY BRIEF CONDUCTED AT THE LZ  PRIOR TO FLIGHT

- HUBBARD ROAD WILL EXPERIENCE INTERMITTENT  CLOSURES

- SEE DRAWING BELOW FOR LOCATIONS OF CLOSURES

- WATER TRUCK IS REQUIRED

- TWO HOMES WILL BE EVACUATED SEE DIAGRAM ALL HOMES WITHIN 300 FT OF OPERATION AREA WILL BE EVACUATED

- THE CONTRACTOR WILL TRIM TREES IF REQUIRED

THE HELICOPTER WILL LAND AT THE LANDINGS ZONE TO CONDUCT A SAFETY BRIEF. WHEN THE LINE CREW IS READY THE GROUND CREW WILL MAKE SURE THE TWO HOMES ARE EVACUATED. ONCE THE AREA IS CLEAR THE STREET CLOSURE CREW WILL CLOSE HUBBARD ROAD. THE HELICOPTER WILL DELIVER EQUIPMENT BAGS TO THE POLE SITES. WHEN THE CREW IS READY FOR THE POLES THE NEW POLES WILL BE SET IN PLACE AND ONCE ALL 5 POLES ARE SET POLE NUMBER ONE CREW SHOULD BE READY TO REMOVE THE OLD POLE. THE REMAINING 4 POLES WILL BE REMOVED IN ORDER. ONCE THE CREW IS COMPLETE THE HELICOPTER WILL REMOVE EQUIPMENT FOR THE POLE SITES. THE EQUIPMENT AND OLD POLES WILL BE RETURNED TO THE LZ STAGING AREA. ONCE THE AIRCRAFT IS CLEAR THE ROAD WILL REOPEN.

2-5-2020

DATE OF SUBMISSION				COMPANY OFFICIAL / TITLE